| # Revision to St. Lawrence College’s Program Development Procedure (Chart) 2018 | St. Lawrence College |
| --- | --- |

# Revision to SLC’s Program Development Procedure (Chart)

Prepared by: Jacqueline Schoemaker Holmes, Program Developer

|  | Step | Person Responsible | Necessary Elements/Actions |
| --- | --- | --- | --- |
|  | 1. Program Idea Submitted | Internal or External Stakeholder | - Program idea submission form - Cross-referenced with historical/recent submissions - Decision made about moving forward with concept paper - If the idea does not proceed, idea originator is informed to close the loop |
|  | 2. Concept Paper | Idea Originator (with assistance from the Program Developer and Institutional Researcher) | - Brief rationale for the program - Program title, campus, delivery, and proposed credential - Program description - Institutional fit/relationship to Strategic Mandate Agreement (SMA) - Information from Program Advisory Committee (PAC) meetings - Competitor data, comparator KPIs, student and workforce demand - Student and employment demand for program - Consultation |
|  | 3. Departmental Dean Review | Program Developer ensures the Dean(s) where the program would fit reviews the program idea in order to identify an Academic Lead for program development | - Relevant Dean(s) are advised and review concept paper - An Academic Lead is identified - Identification of what information is needed for the Strategic Enrolment Management (SEM) Committee |
|  | 4. Strategic Enrollment Management Committee Consultation | Academic Lead and Program Developer | - SEM gathers relevant data/information needed and provides comments for consideration to forward to Dean’s Council |
|  | 5. Preparation of Business Plan | Program Developer | The Business Plan requires: Program description - Identification of any unique program requirements - Comment on proposed modes of delivery - Program of instruction term offering including program hours - Evidence of student demand and community need for the program - Evidence of consultation – both internal and external - Proposed admission requirements - Target enrollments - Draft New Program Proposal Operating Budget Worksheet |
|  | 6. Dean’s Council Review | Academic Lead and Program Developer | - The Concept Paper and Business Plan recommended by SEM are compiled and brought before Dean’s Council for review |

|  | 7. OCQAS-CVS Draft Prepared & Approved as soon as possible | Program Developer | - Consultation with OCQAS and drafting of CVS documents |
| --- | --- | --- | --- |

|  | 8. Academic Council Review | Academic Lead and Program Developer | - CVS application for support and recommendation |
| --- | --- | --- | --- |
|  | 9. College Executive Team Review | Academic Lead and Program Developer |  |

|  | 10. Board of Governors Academic Subcommittee Review | Academic Lead and Program Developer |  |
| --- | --- | --- | --- |
|  | 11. Board of Governors Approval | Academic Lead and Program Developer | CVS Validation Letter |

|  | 12. Ministry Funding Application for Domestic Programs Completed and Submitted | Program Developer | MTCU Funding Application Form |
| --- | --- | --- | --- |
|  | 11. Phase 2 – Curriculum Development Begins | Manager of Curriculum Development |  |